## projects
CPAD Project:
order | project | description | priority | assignee | schedule | status
1
2 | coordinate awos upgrade - site prep, electrical, notam, etc |  | 1
3 |  | coordinate cpaf agreement and funds transfer | 1 | Tina
4 |  | fuel shed clean out and move material to tool shed | 1 |  |  | done
5 |  | site prep excavation and post installation | 1 |  |  | done
6 |  | electrical work contracted and completed | 1 |  |  | done
7 |  | mesotech install and activation | 1 |  |  | done
8 |  | faa inspection and approval | 1
9
10 | maintenance
11 |  | fuel pump maintenance - arrange for filters to be replaced | 1 |  |  | done
12 |  | buy new UPS for light shed with online capability, ability to cycle power remotely | 2
13 |  | install batteries in anti-collision lights on hill | 1
14
15 | sell excess equipment |  | 3
16 |  | dispo old tractor | 3 |  |  | talked with Victor, he will take it back
17 |  | place excess equipment on website for bid to get it sold | 3
18 |  | flail mower, swisher, one of the walk behind mowers | 3
19
20 | install airport signs |  | 1
21 |  | replace rotted posts and break-away features | 1
22 |  | install noise abatement signs | 1
23 |  | identify additional signs needing replacement | 2
28
29 | creek and ditch cleanout
30 |  | excavation to remove sediment in creek bottom at airport entrance |  |  |  | bid received
31 |  | ditch cleanout at all culverts around runway
32
33 | vegetation control and tree removal |  | 2
34 |  | community work days coordination
35 |  | mowing, weeding, cleaning runway of debri, spraying, etc | 1
36 |  | mowing plan and schedule | 2
37 |  | brush clearing and rock removal
38 |  | spread emergent chemicals - fenceline and around lights, taxiway | 1 |  |  | initial application along taxiway (ineffective)
39 |  | remove trees in creek by cameron park blvd |  |  |  | bid received
40 |  | remove trees along alhambra drive
41
42 | gate renewal and maintenance |  | 3
43 |  | distribute new clickers to neighborhood
44 |  | run new wires, reprogramming,
45 |  | lubrication and adjustment preventative maintenance
46
47 | office computer and data management |  | 2
48 |  | website maintenance - compliance with new california law
49 |  | update website with current board members and positions | 1 |  |  | done
50 |  | post meeting minutes and agendas |  |  |  | done
51 |  | develop cloud secure storage and backup solution for office computer
52 |  | 5s office and archive anything not needed for day to day operation |  | Dennie |  | in work
53 |  | update office procedures manual
54 |  | install wifi in office
55
56 | Pavement maintenance and repair |  | 3
57 |  | Airpark Streets repair
58 |  | rough patches at entrance - contact county
59 |  | Airport runway and taxiway repairs
60 |  | chuck walls hangar ramp repair
61 |  | sweep runup areas of small rocks
62 |  | sealcoat and crack pavement plan
63
64 | Community Communication and outreach |  | 3
65 |  | Newsletter, Website
66 |  | Committees, Cops and Rodders event
67 |  | FOCA, Foundation
68
69 | Airport Layout Plan |  | 3
70 |  | Airport Infrastructure Plan, thru the fence plan
71 |  | Airport Diagram, AWOS, FAA Cameras
72 |  | FAA engagement, improvements
73 |  | grant applications
74
75 | financial
76 |  | renters manage payments and invoices
77 |  | audit
78 |  | bill pay - coordinate with book-keeper
79 |  | look at quickbooks for treasurer
80
81 | compliance, inspections
82 |  | fuel system - tanks, environmental
83 |  | fuel pumps wts and measures
84 |  | awos annual inspection
85 |  | etc
86
87 | Vehicles maintenance
88 |  | truck - keys, registration, insurance
89 |  | tractor - keys, paperwork, maintenance plan
90 |  | zero turn mower - keys, paperwork for warranty, maintenance contract
91 |  | contracts for tractor maintenance, mower maintenance
92 |  | walk behind mower keys, maintenance
93 |  | swisher key and maintenance
94 |  | gator atv - keys, maintenance plan
95
96 | weather cameras
97 |  | weather cameras maintained by cpaf. also maintains wireless internet infrastructure
98 |  | - equipment located in fuel shed, office, light shed
99
100 | other/parking lot
101 |  | cal fire base plan
102 |  | draft plan and coordinate with local calfire office
103 |  | drone keepouot zone
104 |  | draft policy, work with faa to generate plan
105 |  | ocular study
106 |  | coordinate with county
107 |  | engagement with county (edc and eid)
108 |  | engagement with faa and caltrans, other gov entities
109 |  | inspections, regulatory compliance
110 |  | capital improvement plans and schedule
111 |  | pavement, pumps, gates, lights, etc
112 |  | replacing the airport manager
113 |  | ad hoc committee - John and Tina have lead |  |  | initial draft complete
114

## actions
date | action | priority | assignee | status
2025-02-24 |  |  |  |  | parking lot
| daily fuel checks |  |  |  | updates to red book
| daily fod checks |  |  |  | hangar rental contact candidates
| awos upgrade coordination |  |  | done
| rentals follow-up |  |  | in work
| financials acct receivable coordinated |  |  | done
| scanner working |  |  | done
signs installed
| creek cleanout |  |  | need bids
emergent spread along fencelines
buy cell phone
buy wireless router
| light shed alarms and reset procedures |  |  | done
board meeting actions and info - posting
computer backup system